## Sheet1
Feature | PBI | Task | Effort(days) | Status
Implement initial architecture | Identify required high level modules |  | 1 | Done
| communicartion model |  | 0.5 | Done
| database design |  | 1 | Done
Implement databse | create databse in SQL server |  | 1 | Done
Implement server project strucuture | impelent required back end project structure |  | 1 | Done
| Identify required data models |  | 0.5 | Done
| Use ORM to map DB (EFCore) |  | 2 | Done
| Identify required REST endpoints |  | 0.5 | Done
| Implement Endpoints | GetItemListByStatus() | 1 | New
|  | GetAllActiveItems | 1 | Done
|  | AddNewItem(Item item) | 1 | Done
|  | GetItemById | 0.5 | Done
|  | GetItemLkstByStatus | 1 | Done
|  | UpdateItem | 1 | Done
|  | GetItemListByMe | 1 | Done
|  | Deleteitem | 1 | Done
|  | Login | 1.5 | Done
|  | Register | 1.5 | Done
|  | GetAllUserTypes | 0.5 | Done
|  | GetUserType | 0.5 | Done
|  | UserValidate | 0.5 | Done
|  | AddNewBid | 1 | Done
|  | UpdateBid | 1 | New
| read about jwt autherntication |  | 1 | Done
| Implement Authentication (JWT) in server side |  | 2 | Done
| Implement tests | Add test projects | 0.5 | New
|  | implement tests for endpoints | 5 | New
Implement front end | Create project structure(ReactJS) |  | 0.5 | Done
| implement Login UI Component |  | 2 | Done
| implement Register UI Component |  | 2 | Done
| implement routing |  | 0.5 | Done
| implement communication with backend enpoint |  | 1.5 | Done
| implement Item Component | Implement UI to List the Active items | 1 | Done
|  | Implement UI to List the All items (ADMIN) | 1 | Done
|  | Paging to item list(ADMIN) | 1 | New
|  | Filter item list by status(ADMIN) | 1 | Started
|  | show latest bid in every active bid in the List() | 1 | Done
|  | Update item status to NEW-->Active(ADMIN) | 1 | Done
|  | Auto change New to active at scheduled time(ADMIN) | 1 | New
|  | Delete item which are not Active.sold/unsold(ADMIN) | 1 | New
|  | edit items not active/sold/unsold | 1 | New
|  | Load images for every item in react list | 1 | New
|  | UI to Add new item using modal (ADMIN) | 1.5 | Done
|  | show countdown for every item | 1 | New
|  | Enable to same images for the item | 1 | New
|  | see item list I bid | 1 | New
|  | see details of items I bid | 1 | New
| Implement Bid Component | implement UI to add new bid for an item | 1 | Done
|  | Add new bid if outbid | 1 | New
Implement Notification system | Identify design for Notification
| Investigate about signalR |  | 2 | New
| Design notification model |  | 2 | New
| Implement notification model |  | 3 | New
| Notified if higher bid is added to item while adding bid |  | 2 | New
| Notified if outbid my bid |  | 2 | New
| Notify when auction is over | implement schedular to run daily and get finished bids info-serverside | 2 | Started
|  | Notify all the applicants of selected bids | 1 | New